Capstone Project Report

Report 2 – Project Management Plan

– Hanoi, August 2026 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	4

1.3 Project Risks	4

2. Management Approach	5

2.1 Project Process	5

2.2 Quality Management	5

2.3 Training Plan	5

3. Project Deliverables	5

4. Responsibility Assignments	5

5. Project Communications	6

6. Configuration Management	6

6.1 Document Management	6

6.2 Source Code Management	6

6.3 Tools & Infrastructures	6

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 14/08/2026 | A | BE Team | Initial Project Management Plan authored from the current, already-implemented system's real scope — companion to Reports 1/3/4. Responsibility-assignment columns and training-plan participants are role-based placeholders pending the team's real names from Report 1 §1.2. |
| 15/08/2026 | M | Hà Đông Hải | Rebuilt for whole-platform scope: WBS extended with frontend, UI/UX design, deployment and documentation work (488 man-days); responsibility matrix re-keyed to the real four-member team with frontend and deployment ownership; Azure delivery platform and frontend/test tooling added; quality and configuration-management practices widened to both tiers. |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | Auth & Account Management |  |  |
| 1.1 | Register/verify/login, Google OAuth, JWT + policy-based authorization | Complex | 12 |
| 1.2 | Forgot/reset password, profile edit, ID verification upload | Medium | 6 |
| 1.3 | DSAR data export & erasure (anonymise-in-place) | Medium | 5 |
| 2 | Venue Management |  |  |
| 2.1 | Venue CRUD, business license/photo upload | Medium | 6 |
| 2.2 | Seating-zone drag-and-drop editor (2D/3D) | Complex | 10 |
| 2.3 | 360° virtual tour (scene/hotspot editor + Auto-Stitch integration) | Complex | 14 |
| 2.4 | Staff assignment, venue gallery, custom criteria | Medium | 7 |
| 3 | Admin Venue Approval & Content Moderation |  |  |
| 3.1 | Venue approve/reject queue | Simple | 3 |
| 3.2 | AI-assisted (Gemini) show/livestream moderation queue | Complex | 10 |
| 4 | Show Management |  |  |
| 4.1 | Show CRUD, performer line-up builder | Medium | 8 |
| 4.2 | Show lifecycle (submit/publish/reschedule/format-change/cancel) | Complex | 10 |
| 4.3 | Ticket tiers, pricing windows, AI poster generation | Medium | 8 |
| 4.4 | Legal & royalty declaration | Simple | 2 |
| 5 | Ticketing |  |  |
| 5.1 | Ticket hold (15-min), quota management | Medium | 6 |
| 5.2 | VNPay payment integration, QR generation | Complex | 10 |
| 5.3 | Transfer, cancellation, refund request workflow | Medium | 8 |
| 5.4 | Walk-in sale & door check-in (Staff) | Medium | 7 |
| 6 | Livestream |  |  |
| 6.1 | Mux/Cloudflare integration + LivestreamServiceFactory, start/end broadcast | Complex | 12 |
| 6.2 | SignalR access-gated viewing room, chat, viewer count | Complex | 12 |
| 6.3 | Concurrent-device session limiting | Medium | 5 |
| 7 | Donation & Financial Ledger |  |  |
| 7.1 | Donate flow, owner acknowledgement, performer payout | Complex | 11 |
| 7.2 | Double-entry ledger (LedgerJournalFactory), reconciliation job | Complex | 12 |
| 7.3 | Settlement (2-tranche release), public donation ticker/feed | Complex | 11 |
| 8 | F&B Ordering |  |  |
| 8.1 | Menu CRUD, mobile ordering flow | Medium | 6 |
| 8.2 | Staff order board (status progression) | Simple | 4 |
| 9 | Subscription & Billing |  |  |
| 9.1 | Plan CRUD (Admin), subscribe/renew/cancel (Owner) | Medium | 7 |
| 10 | Complaints & Venue Penalties |  |  |
| 10.1 | Complaint file/lookup/resolve (incl. guest path) | Medium | 7 |
| 10.2 | Venue penalty issue/appeal/auto-overturn workflow | Medium | 7 |
| 11 | Recommendation & Personalisation |  |  |
| 11.1 | Behaviour logging, event scoring, AI hybrid recommender | Complex | 12 |
| 11.2 | Follow/wishlist/rating | Simple | 4 |
| 12 | Notifications |  |  |
| 12.1 | FCM push integration, notification inbox, SpeedSMS integration | Medium | 8 |
| 13 | Admin Back-Office |  |  |
| 13.1 | User management, bank-account verification, ledger integrity check | Medium | 8 |
| 13.2 | Taxonomy & subscription-plan management, platform analytics | Medium | 6 |
| 14 | Cross-Cutting Platform Work |  |  |
| 14.1 | Clean Architecture scaffold, CQRS/MediatR pipeline, generic repository/UoW | Complex | 10 |
| 14.2 | 29 Hangfire background jobs (SLA/expiry/settlement/security-monitoring) | Complex | 14 |
| 14.3 | Security hardening (ASVS-based audit + fixes), legal/compliance mapping | Complex | 12 |
| 14.4 | Test suite (unit/integration), documentation | Complex | 15 |
| 15 | Frontend Implementation |  |  |
| 15.1 | FE: Auth & Account — sign up/verify/login screens, Google OAuth button, forgot/reset password, profile edit, ID upload, DSAR export/erase UI | Medium | 10 |
| 15.2 | FE: Venue Management — venue CRUD forms, seating-zone drag-and-drop 2D/3D editor, 360° tour scene/hotspot builder, staff assignment, gallery uploader | Complex | 18 |
| 15.3 | FE: Admin Venue Approval & Moderation — approval queue, AI moderation review queue | Medium | 6 |
| 15.4 | FE: Show Management — show CRUD wizard, performer line-up builder, ticket tier/pricing editor, AI poster UI | Complex | 10 |
| 15.5 | FE: Ticketing — browse/purchase flow, hold countdown, VNPay redirect, QR ticket, transfer/cancel/refund, Staff walk-in POS + QR scanner | Complex | 14 |
| 15.6 | FE: Livestream — gated viewing room player, chat, viewer count, broadcast control panel | Complex | 12 |
| 15.7 | FE: Donation & Ledger — donate widget, public donation ticker, payout dashboard, ledger views | Medium | 9 |
| 15.8 | FE: F&B Ordering — mobile menu/cart/order tracking, Staff kitchen/counter board | Medium | 8 |
| 15.9 | FE: Subscription & Billing — plan CRUD (Admin), subscribe/renew/cancel (Owner) | Medium | 5 |
| 15.10 | FE: Complaints & Penalties — guest complaint form/lookup, resolve queue, appeal UI | Medium | 6 |
| 15.11 | FE: Recommendation & Personalisation — personalised feed, follow/wishlist, rating UI | Medium | 5 |
| 15.12 | FE: Notifications — inbox UI, push permission prompts | Simple | 4 |
| 15.13 | FE: Admin Back-Office — user management, bank-verification queue, taxonomy UI, analytics dashboard | Medium | 10 |
| 15.14 | FE: Cross-Cutting — design system/component library, routing/auth-guard scaffold, API client + state mgmt, responsive/theming | Complex | 12 |
| 16 | UI/UX Design |  |  |
| 16.1 | Design system & style guide ("Warm Luxury Lounge") | Medium | 4 |
| 16.2 | Stitch briefs per surface (5 surfaces) + view catalog + screens-flow diagrams | Complex | 8 |
| 16.3 | High-fidelity mockups per view (iterative) | Complex | 10 |
| 17 | Deployment & Hosting |  |  |
| 17.1 | Host + deploy (API, DB, panorama-stitcher microservice), domain/SSL setup | Medium | 6 |
| 18 | Documentation |  |  |
| 18.1 | Domain/architecture docs (docs/01-24) | Medium | 6 |
| 18.2 | 7 SEP490 capstone reports | Complex | 10 |
|  | Total Estimated Effort (man-days) |  | 488 |

### 1.2 Project Objectives

Deliver a working, multi-surface MusicLounge platform — backend REST/SignalR API, all 5 client surfaces (Audience Web, Owner Web, Admin Web, Staff Mobile, Audience Mobile F&B), and a deployed/hosted instance — that a review committee can exercise end-to-end across all 4 roles (Audience, Owner, Staff, Admin) by the end of the capstone semester, built to a standard that would survive a real production-readiness review, not just a demo.

Time: fit the full WBS in §1.1 inside the semester's available calendar, sequenced so that every domain's happy path (see Report 3 §2.2 Use Cases) is functional well before the final weeks, leaving the last 2–3 weeks for hardening, security/performance review, and documentation rather than first-time feature work.

Cost: effort is a fixed team-capacity budget rather than a monetary one — the WBS in §1.1 sums to ~488 man-days spanning backend, frontend, UI/UX design, deployment and documentation, delivered by the four-member team named in Report 1 §1.2 across the capstone semester (see Milestone Timeliness and Allocated Effort below for the phase split).

Quality

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Reviewing | 100% of PRs | — | — | Every change reviewed against the project's own backend-code-review-sop before merge. |
| 2 | Unit Test | Domain + Application layers | — | ≤ 5% flaky | Business logic tested with no database — see Report 5. |
| 3 | Integration Test | Every Application handler with DB interaction | — | 0 known-broken at release | Run against SQLite in CI, and against real SQL Server before each major milestone (a real bug has already been caught this way that SQLite alone missed). |
| 4 | Security Audit | OWASP ASVS 5.0.0 checklist, ~350 requirements | — | 0 open BLOCKER | See the project's ongoing role-security-asvs-audit trail. |
| 5 | Release Gate | Full SDLC role-charter sweep (17 roles) | — | 0 open BLOCKER | sdlc-release-gate — first full run (2026-08-09) returned NO-GO with 7 verified blockers, all since resolved. |

Milestone Timeliness (%): ≥ 90% of sprint-end milestones delivered on the date committed at sprint planning.

Allocated Effort (man-days): Requirement/Design 18% · Coding (Backend + Frontend) 62% · Testing 12% · Documentation 8% (of the ~488 man-day total in §1.1).

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | VNPay sandbox behaves differently from the production gateway (IPN timing/retry semantics in particular) — an integration that passes sandbox testing could still surface a bug against the real gateway. | High | Medium | Build the IPN handler to be idempotent and safe against out-of-order/duplicate delivery regardless of sandbox-observed behaviour, rather than coding to the sandbox's specific timing; treat any production VNPay integration as a distinct, separately-tested milestone if the project ever needs one. |
| 2 | SQLite (used in the CI/integration test suite) and the real target engine (SQL Server) diverge on specific behaviours — multi-path cascade delete rules and enum-string-column constraints in particular. A test suite that is 100% green on SQLite is not proof of correctness against the real database. | High | High | Already materialised once — a real SQL-Server-only bug slipped past 287 passing SQLite-based tests. Mitigation in place: run the full suite against a real SQL Server instance before every major milestone/release, not only in the SQLite-backed CI default. |
| 3 | Third-party AI dependency (Gemini) for content moderation, poster generation, and recommendation scoring — an API outage, quota exhaustion, or pricing/policy change is outside the team's control. | Medium | Medium | Moderation and recommendation are both designed to degrade gracefully (a Circuit Breaker pattern around the AI HTTP client falls back to a neutral score rather than blocking the request); poster generation additionally has a second provider (OpenAI) wired as an alternate adapter behind the same interface. |
| 4 | The panorama-stitching feature depends on native OS-level image-processing binaries (OpenCV/Hugin) that can behave differently across the development machine and the eventual deployment target. | Medium | Medium | Kept as a separate out-of-process Python microservice called over HTTP specifically to isolate this native-binary risk from the main .NET host — a stitching-service failure degrades one feature, not the whole API. |
| 5 | There is no self-service path to create an Admin account, and the system is designed so that only one or a few Admin accounts are expected to exist — an Admin's account being locked out, or the one available reviewer/grader Admin credential being lost, blocks a large surface of manual testing. | Medium | Low | Document the Admin-provisioning (direct database insert) procedure clearly for the team and the supervisor before the review/demo date; keep at least one known-good Admin credential recorded outside of any single team member's personal notes. |
| 6 | Livestream infrastructure (Mux/Cloudflare Stream) is a paid third-party service with its own account/billing setup — running out of trial credit or hitting a rate limit close to a demo date would visibly break the platform's most impressive feature. | Medium | Low | Confirm provider account status and quota headroom explicitly ahead of the final demo, not only during regular development. |
| 7 | Team members' familiarity with Clean Architecture, CQRS/MediatR and EF Core varies — a member new to the pattern can introduce a change that quietly breaks the dependency rule (e.g. Domain referencing Infrastructure) or bypasses the Unit-of-Work transaction boundary. | Medium | Medium | Addressed by the Training Plan in §2.3 and by mandatory PR review against the architecture's own conventions before merge. |
| 8 | Scope creep — the domain has more genuinely useful features than one semester can safely absorb (the platform already spans 28 Application feature areas). | Medium | Medium | WBS in §1.1 is the scope contract for the semester; new feature requests during the semester are logged and prioritised against it rather than added ad hoc. |
| 9 | Frontend implementation is significantly behind backend at the time of this plan (2 of 73+ screens built) — most of the remaining ~129 FE man-days is concentrated in the second half of the semester, creating schedule pressure if design handoff (Stitch briefs) or screen wiring takes longer than estimated. | High | Medium | Track FE progress against the WBS in §1.1 as its own burndown, separate from backend's (which is already largely complete); reprioritise screens by role-criticality (Audience ticket purchase, Owner venue/show management) over nice-to-have surfaces (recommendation/rating) if time runs short. |

## 2. Management Approach

### 2.1 Project Process

Scrum, with weekly sprints aligned to the capstone's supervisor check-in cadence: sprint planning at the start of the week, a working demo at the end of it, and a short retro before the next planning session. The WBS in §1.1 is the product backlog; each WBS leaf item is broken into 1–3 sprint tasks at planning time.

Sprint 1–2: project scaffold (4-project Clean Architecture, CI, database migrations pipeline), backend Auth, UI/UX design system + Stitch briefs for all 5 surfaces. Sprint 3–6: backend Venue/Show/Ticketing (the core marketplace loop) in parallel with frontend Auth + Venue screens. Sprint 7–9: backend Livestream/Donation & Ledger — the most architecturally complex area, sequenced after the core loop is stable — in parallel with frontend Show/Ticketing screens. Sprint 10–11: backend F&B/Subscription/Complaints/Admin back-office, frontend Livestream/Donation screens. Sprint 12–13: frontend F&B/Subscription/Complaints/Admin back-office screens, cross-cutting hardening (security audit, background-job reliability). Sprint 14–15: deployment/hosting setup, final regression against real SQL Server, demo rehearsal, documentation and report writing.

### 2.2 Quality Management

Five practices, applied continuously through every sprint rather than only at the end of the semester:

•  Defect Prevention — a fixed set of conventions per tier, enforced at review rather than discovered in testing: on the backend, repository/Unit-of-Work access only from handlers, no direct DbContext use in the Api layer, and every command covered by a FluentValidation validator; on the frontend, shared design-system components instead of one-off markup, server state owned by TanStack Query rather than hand-rolled effects, and no screen shipping without its loading, empty and error states designed.

•  Reviewing — every pull request reviewed against the project's own documented code-review standard operating procedure before merge; no direct pushes to the main branch.

•  Unit Testing — backend Domain and Application logic tested without a database, and frontend components tested in isolation against a mocked API with React Testing Library, so a broken business rule or a broken screen state is caught before integration testing runs.

•  Integration Testing — real handler-to-database round trips, run in CI against SQLite for speed and, before every major milestone, again against a real SQL Server instance to catch the class of bug SQLite cannot reproduce (see Risk #2).

•  System Testing — automated Playwright journeys plus manual walkthroughs of each actor's golden path (Audience, Owner, Staff, Admin) against the deployed Azure staging environment, together with a security pass against the OWASP ASVS 5.0.0 checklist, an accessibility pass against WCAG 2.2 Level AA, and a load pass against realistic peak shapes (ticket on-sale spikes, concurrent livestream viewers).

### 2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Clean Architecture & CQRS/MediatR | Any member new to the pattern | Sprint 1, ~1 day | Waived if the member has prior CQRS/MediatR project experience |
| EF Core + SQL Server (migrations, indexing, transactions) | Any member new to EF Core | Sprint 1–2, ~1 day | Waived if the member has prior EF Core project experience |
| Git / GitHub workflow (branching, PR review) | All members | Sprint 1, ~0.5 day | Mandatory |
| OWASP ASVS 5.0.0 basics | Whoever leads the security-review sprint task | Before Sprint 12 | Mandatory for that task's owner only |
| React + TypeScript + Tailwind CSS (frontend stack) | Any member new to the stack | Sprint 2-3, ~1 day | Waived if the member has prior React/TS project experience |

## 3. Project Deliverables

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | Project Schedule / Tracking (Report 2 companion) | End of semester | Kept live sprint-by-sprint, finalised at submission. |
| 2 | Product Backlog / WBS (this report §1.1) | Sprint 1, revised each sprint | Scope contract for the semester. |
| 3 | Source Code (backend repository) | End of semester | MusicLounge-Backend — 4-project Clean Architecture solution. |
| 4 | Database Scripts (EF Core migrations) | End of semester | Code-First — no hand-written DDL. |
| 5 | Report 1 — Project Introduction | End of semester | This report set. |
| 6 | Report 3 — Software Requirement Specification | End of semester | — |
| 7 | Report 4 — Software Design Document | End of semester | — |
| 8 | Report 5 — Test Documentation, Test Report, Unit Test | End of semester | — |
| 9 | Report 6 — Software User Guides | End of semester | — |
| 10 | Report 7 — Final Project Report | End of semester | Aggregates Reports 1–6. |
| 11 | Defects List | End of semester | Tracked continuously; see Report 5 Test Report. |
| 12 | Presentation Slide Deck | Demo date | — |
| 13 | Source Code (frontend repository) | End of semester | fontend/Fontend_Final — Vite + React + TypeScript + Tailwind. |
| 14 | Deployed/Hosted Platform (live instance) | End of semester | Publicly reachable URL for the review committee to exercise end-to-end. |

## 4. Responsibility Assignments

Columns use the team members named in Report 1 §1.2. Each row names exactly one owner (D) so accountability is never split, with a named reviewer (R) for every deliverable that leaves the team.

D~Do; R~Review; S~Support; I~Informed; <blank> = Not involved

| Responsibility | Hải (Leader) | Nhiên | Khoa | Phúc |
| --- | --- | --- | --- | --- |
| Project planning & tracking (WBS, sprint plan, risk register) | D | S | S | S |
| Requirement analysis & specification (Report 1, Report 3) | R | D | S | S |
| UI/UX design system, Stitch briefs, view catalogue | S | D | R | I |
| Solution architecture & Report 4 (SDD) | D | R | S | S |
| Backend — platform scaffold, CQRS pipeline, shared infrastructure | D | S | S | R |
| Backend — Auth, Venue, Show, Ticketing | R | D | S | S |
| Backend — Livestream, Donation, Payment & Ledger | D | S | R | S |
| Backend — F&B, Subscription, Complaints, Admin back-office | R | S | D | S |
| Backend — background jobs & security hardening | R | I | S | D |
| Frontend — Audience Website | S | D | R | I |
| Frontend — Owner Web Dashboard | R | S | D | S |
| Frontend — Admin Web Console | S | R | S | D |
| Frontend — Staff Mobile & Audience Mobile F&B apps | D | S | S | R |
| Test design, automation & execution (Report 5) | R | S | S | D |
| Deployment to Azure, CI/CD pipeline, environment configuration | D | I | S | R |
| Documentation & user guides (Report 6) | S | R | I | D |
| Final integration, Report 7, demo rehearsal | D | S | S | S |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Sprint Planning | Whole team + Supervisor | Agree the sprint's WBS items and acceptance criteria | Weekly, start of sprint | In-person/online meeting |
| Sprint Demo & Retro | Whole team + Supervisor | Show working software, review what did/didn't go well | Weekly, end of sprint | In-person/online meeting + a running instance |
| Daily Sync | Whole team | Quick blockers/progress check | Daily, ~15 min | Chat channel (async) or short call |
| Code Review | PR author + reviewer(s) | Catch defects and architecture-convention drift before merge | Continuous, per pull request | GitHub pull request comments |
| Supervisor Check-in | Leader + Supervisor | Escalate risks, confirm scope decisions | As needed, at minimum bi-weekly | Email / scheduled meeting |
| Incident/Defect Reporting | Whole team | Log and triage a found defect | As found | Issue tracker |

## 6. Configuration Management

### 6.1 Document Management

All narrative project documentation lives in this repository's docs/ folder in Markdown, version-controlled alongside the code it describes so a documentation change and the code change it documents land in the same review — the alternative (a separate wiki or shared drive) drifts out of sync with the code far more easily.

The 7 formal SEP490 report documents (this set) are generated from that same docs/ source-of-truth into the official .docx templates and kept in spec/generated/, so every report can be regenerated after a scope or design change instead of hand-edited out of sync with the underlying docs.

Every substantive document change is recorded in that document's own "Record of Changes" table (§I of every report) — Added/Modified/Deleted, who, and why — rather than relying on git history alone, since a reviewer opening only the .docx should still see its own change log.

### 6.2 Source Code Management

Git, hosted on GitHub, across the platform's repositories — the backend API solution, the frontend client applications, and the panorama-stitching microservice. Trunk-based development off a single main integration branch in each, with short-lived feature branches per WBS task merged via pull request; no long-lived per-developer branches that could drift far from main. A change spanning tiers (a new endpoint plus the screen that consumes it) is raised as linked pull requests reviewed together, so the API contract and its consumer never merge out of step.

Every pull request requires at least one review before merge (see §2.2 Quality Management); the CI pipeline runs the unit/integration test suite on every PR, and merge is blocked on a red build.

Database schema changes are EF Core Code-First migrations only, committed alongside the entity/configuration change that caused them — there is no hand-written DDL and no schema drift between environments that migrations don't already capture.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Backend Framework | ASP.NET Core 8 (C#), Clean Architecture (Domain / Application / Infrastructure / Api) |
| Application Patterns | MediatR (CQRS), FluentValidation, Generic Repository + Unit of Work |
| Database & ORM | SQL Server 2022 (Azure SQL Database in the deployed environments) · SQLite for CI-speed integration tests · Entity Framework Core 8 (Code-First migrations) |
| Background Jobs | Hangfire with SQL Server storage — 30 job classes, 22 of them on recurring schedules |
| Real-Time | SignalR — livestream chat and access gating, public donation ticker |
| Frontend — Web | React 18 + TypeScript 5 + Vite 5 + Tailwind CSS 3; TanStack Query for server state, React Router for navigation |
| Frontend — Mobile | React Native + TypeScript (Staff Mobile, Audience Mobile F&B); React Navigation; shared API client with the web surfaces |
| UI/UX Design | Stitch (AI-assisted UI generation) driven from per-surface design briefs; a shared “Warm Luxury Lounge” design system and component library |
| Payment | VNPay (sandbox environment) |
| Livestream | Mux and Cloudflare Stream, selected at runtime behind a provider factory |
| AI Services | Gemini (moderation scoring, poster generation, recommendation feature scoring); OpenAI as an alternate poster-generation provider |
| Notifications | Firebase Cloud Messaging (push) · SpeedSMS (SMS, Vietnam) · SMTP (email) |
| Auxiliary Microservice | Python / OpenCV + Hugin panorama-stitching service for venue 360° tours, called over HTTP |
| Cloud Platform | Microsoft Azure — App Service (API), Azure SQL Database, Container Apps (stitching microservice), Static Web Apps (three web surfaces), Blob Storage + CDN (uploads and media), Key Vault (secrets), Application Insights + Monitor (telemetry and alerting) |
| Source Control & CI/CD | Git / GitHub with pull-request-gated GitHub Actions — build, test, then deploy to Azure on merge |
| Testing | xUnit + FluentAssertions (backend) · Vitest + React Testing Library (web) · Jest + React Native Testing Library (mobile) · Playwright (end-to-end) · k6 (load) |
| API Documentation | Swagger / OpenAPI interactive documentation |
| Project & Document Tooling | Markdown documentation in docs/, generated into the official SEP490 .docx report templates |